## Project Plan
Produced as part of the Nottinghamshire LPS Implementation Steering Group, making use of members' individual organisation project plans, as well as ones shared from Greater Manchester, Derbyshire County Council and Rotherham, Doncaster and South Humber NHS Foundation Trust. This project plan will be updated on an iterative basis and at no stage is intended to be ‘definitive’. If you believe any of the content to be inaccurate or if you believe there is further information that could enhance its usefulness then please do get in contact: Elaine Dower (elaine.dower@nhs.net, 07342 081522).
Key area | Detailed steps - consider everything from children and adult perspective | NHS Providers | CCG/ICB | Local Authority | Ambulance Trust | Independent Hospital | Care Home | Other Social Care Providers | Lead | Before finalisation of Code and Regs | Post finalisation of Code and Regs | Prior to Initial Implementation | Prior to Phase 2 implementation | Prior to Phase 3 implementation | Ongoing
01. Scoping | Obtain numbers of current DoLS applications | x | x | x |  | x | x | x |  | x
01. Scoping | Obtain numbers of current CoP deprivation of liberty/Re X applications | x | x | x |  | x | x | x |  | x
01. Scoping | Local Authority to share with CCG(s) of number of care home DoLS / applications not yet processed / COP approved DoLs in the community who are CHC funded |  | x | [6 empty] | x
01. Scoping | Identify the likely gaps in these numbers (eg 16/17 year olds, liberal use of Ferreira, community - own home, supported living) | x | x | x |  | x | x | x |  | x
01. Scoping | Establish additional criteria for scoping - ideally consistent across ICS | x | x | x |  | x | x | x |  | x
01. Scoping | Establish indications for objection to residing at the place or to receiving care and treatment at that place (for scoping purposes - will potentially need to be revised in light of code) - ideally consistent across ICS | x | x | x |  | x | x | x |  | x
01. Scoping | Obtain likely numbers on the basis of criteria for total LPS applications and those 'objecting' (reasonable to believe) (requiring an AMCP) | [8 empty] | x
01. Scoping | CHC vs s117 - discuss protocol for dealing with these if criteria for both are met |  | x | x | [5 empty] | x
01. Scoping | Self- funders in community/care homes - discuss protocol for dealing with these cases |  |  | x |  |  | x | x |  | x
01. Scoping | As the CCG with be responsible body for those that are full CHC only, ensure there are robust processes for verifying, scrutinising and challenging decision making as to whether CHC or joint funded. |  | x | x | [5 empty] | x
01. Scoping | Complete the NHSE/I return by 25 September |  | x | [6 empty] | x
02. Project | Identify a lead within the organisation, with responsibility for ensuring a smooth transition between DoLS and LPS | x | x | x |  | x | x | x |  | x
02. Project | Identify individuals from different departments assigned to project team (likely to include specific reps from Children's services, HR, Learning & Development, Data/Business Intelligence/IT) | x | x | x |  | x | x | x |  | x
02. Project | Establish a project group and develop ToR | x | x | x |  | x | x | x |  | x
02. Project | Identify administrative support for the project/project group | x | x | x |  | x | x | x |  | x
02. Project | Identify how risks will be captured and feed into organisational risk escalation and management processes | [8 empty] | x
02. Project | Ensure organisational representation on any Place-wide or ICS-wide implementation networks | x | x | x | x | x | x | x |  | x
02. Project | Regularly update project plan as more information available | x | x | x |  | x | x | x |  | x | x | x | x | x
02. Project | Feed into the national consultation process | x | x | x | x | x | x | x |  | x
03. Implementation Networks | Make contact with reps from other partner organisations | x | x | x | x | x | x | x |  | x
03. Implementation Networks | Agree membership and terms of reference of LPS Implementation Group | x | x | x | [5 empty] | x
03. Implementation Networks | Feed into the national consultation process | x | x | x | [5 empty] | x
03. Implementation Networks | Identify aspects of LPS where it would be more efficient / effective to work at a wider level (across all ICP partners, across all ICP Responsible Bodies, across all NHS responsible Bodies, across all Place bodies etc) (see: 'LPS - Questions for ICS/ICP') | x | x | x | [5 empty] | x
03. Implementation Networks | Discuss if there are some aspects it would be beneficial to work with other ICS areas on eg development / commissioning of training | x | x | x | [5 empty] | x
04. Electronic System | Identify if there is a desire (however idealistic) to have a single electronic system at an ICP level to record LPS to support their portability (see: 'LPS - Questions for ICS/ICP') | x | x | x | x | x | x | x |  | x
04. Electronic System | Identify ability of current electronic system to be updated to capture relevant LPS information and add any additional fields needed for the national minimum data set | x | x | x | x | x | x | x |  | x
04. Electronic System | Identify the potential (and costs) for electronic system to be accessible to others outside of the organisation | x | x | x | [5 empty] | x | x
04. Electronic System | Identify if there is the possibility of obtaining access to the relevant NHS systems (SystmOne/EMIS for GP practices) to gather direct information on mental disorder |  | x | x | [5 empty] | x | x
04. Electronic System | Identify other organisations who use the same electronic system to combine and lobby system provider to change/reduce fees | x | x | x |  | x | x | x |  | x
04. Electronic System | Obtain advice on the legality of information sharing agreements (between the organisations wishing to share a system) | x | x | x |  | x | x | x |  |  | x | x
04. Electronic System | Where current systems cannot meet desired requirements examine the possibility of an alternative (eg if multi-agency, a web hosted database with secure log in - this could be developed through TIAN or an individual organisation database but centrally produced and shared so all organisation keeping the same data in the same format) | x | x | x | [5 empty] | x | x | x
04. Electronic System | Incorporate statutory and non-statutory forms into electronic system for electronic completion | x | x | x | x | x | x | x |  |  |  | x
05. Administration | Identify if there is a desire (however idealistic) to have a single shared administrative function for LPS to create efficiency (see: 'LPS - Questions for ICS/ICP') | x | x | x | [5 empty] | x
05. Administration | Design admin processes (including sending Authorisation documentation within 72 hours - para. 16(2)) | x | x | x |  | x | x | x |  | x | x
05. Administration | Identify administrative tasks (see: 'LPS - Process andprocedure questions'), learning from Local Authorities and MHA Admin Teams | x | x | x |  | x | x | x |  | x | x
05. Administration | Identify forms that need to be developed and approved (non-statutory) | x | x | x | [5 empty] | x | x
05. Administration | Produce draft forms for approval | x | x | x | [6 empty] | x
06. Approval of AMCPs | Identify likely numnbers of AMCPs required across LA area - will need organisational estimates from health partners as well |  |  | x | [5 empty] | x
06. Approval of AMCPs | Produce approval guidelines for AMCPs (as per para. 39a) |  |  | x | [5 empty] | x | x
06. Approval of AMCPs | Speak to neighbouring Local Authorities about out of area AMCPs - reciprocal arrangements? |  |  | x | [5 empty] | x | x | x
07. Governance | As required, produce strategic briefings showing overall LPS plan and progress for Senior Executive/ Board/Governing Body | x | x | x | x | x | x | x |  | x | x | x | x | x
07. Governance | Feed into Place-wide and ICS-wide Local Implementation Networks | x | x | x | x | x | x | x |  | x | x | x | x | x
07. Governance | Ensure risks identified are being managed according to organisational risk escalation and management processes | x | x | x | x | x | x | x |  | x | x | x | x | x
08. IMCAs | Scope numbers of IMCAs potentially needed - for those cases where no appropriate person + cases where appropriate person may request/benefit from an IMCA | x | x | x | [5 empty] | x
08. IMCAs | Identify if there is a desire to have a single IMCA service contract for MCA and LPS across the ICS/ICB partners (see: 'LPS - Questions for ICS/ICP') | x | x | x | [5 empty] | x
08. IMCAs | Commission IMCA service (to meet duties para. 41-43) | x | x | x | [6 empty] | x | x
08. IMCAs | Liaise with neighbouring areas re out of area IMCAs - reciprocal arrangements? |  | x | x | [5 empty] | x
09. Process/procedure | Dependent on decisions re aspects of LPS being managed at an LPS hub (ICS or ICB partners), identify the extent to which procedural guidance can be shared | x | x | x | x | x | x | x |  | x
09. Process/procedure | Develop process maps/flowcharts for cared-for person flow through the process for different variables (see: 'LPS - Process and procedure questions') | x | x | x | x | x | x | x |  | x | x
09. Process/procedure | Agree with Independent Hospitals the referral process |  |  | x | [5 empty] | x | x
09. Process/procedure | Agree with Responsible Body partners process and requirements for transferring an LPS authorisation between agencies | x | x | x | [5 empty] | x | x | x
09. Process/procedure | Have legality of procedural documents checked | x | x | x |  | x | x | x |  |  |  | x
09. Process/procedure | Update related policies, procedures and guidance | x | x | x |  | x | x | x |  |  | x | x | x | x | x
10. MH Assessments | Inpatient hospital settings - ensure part of medic's role to record diagnosis of mental disorder and update paperwork to ensure there is a specific place to record this | x |  |  |  | x |  |  |  | x
10. MH Assessments | Review of GP contracts to determine extent to which GPs can be requested to provide information to support determination of mental disorder for community cases (non-complex only?) |  | x | [6 empty] | x
10. MH Assessments | Ensure commissioning procedures for LPS Mental Health Assessors (when other assessments, including GP records, not available) meet regulations |  | x | x | [6 empty] | x
11. MC Assessments | Identify circumstances in which there may not be an individual suitably qualified to complete a mental capacity assessment as part of the cared-for person's pathway |  |  | x | [5 empty] | x
11. MC Assessments | Ensure commissioning arrangements for LPS Mental Capacity Assessors meet regulations |  |  | x | [6 empty] | x
13. Staffing | From scoping determine likely numbers of pre-authorisation reviewers (non-AMCPs), AMCPs, Authorisers | x | x | x | [5 empty] | x
13. Staffing | Consider if any likely workforce implications of s.21za appeals | x | x | x | [5 empty] | x
13. Staffing | Update (as necessary) Job Descriptions of clinical staff who may be completing medical assessments of mental disorder, mental capacity assessments or necessary and proportionate assessments. | x | x | x | x | x | x | x |  | x | x
13. Staffing | Decide banding/grading of: a)pre-authorisation reviewers (non-AMCP), b)AMCPs, c)Authorisers, d)Admin | x | x | x | [5 empty] | x | x
13. Staffing | Write Job Descriptions | x | x | x | [5 empty] | x | x
13. Staffing | Commence recruitment procedures | x | x | x | [5 empty] | x | x | x
14. Training | Identify current numbers of BIAs | x | x | x |  | x | x | x |  | x
14. Training | Review current MCA training - is it effective? | x | x | x |  | x | x | x |  | x
14. Training | Develop LPS training needs analysis to cover: all staff (awareness), staff who will be expected to identify a DoL, staff who will be undertaking assessments/determinations, pre-authorisation reviewers, AMCPs, Administrators, Authorisers, Legal Teams | x | x | x | x | x | x | x |  | x
14. Training | Book places on BIA to AMCP conversion training | x | x | x | [5 empty] | x
14. Training | Determine which training can be delivered in house and which will need commissioning | x | x | x | x | x | x | x |  | x
14. Training | Work with partners to determine training that could be jointly commisisoned/delivered | x | x | x | x | x | x | x |  | x
14. Training | Determine your obligations to provide training to organisations from whom you commission services |  | x | x | [5 empty] | x
15. Communications | Produce internal comms 'strategy' for LPS - identfy which teams will need what level of information | x | x | x | x | x | x | x |  | x
15. Communications | Communication with organisations reporting into your responsible body (care homes, independent hospitals, hospices) | x | x | x | [5 empty] | x | x | x | x | x | x
15. Communications | Produce awareness raising posters for both clinical/ staff areas | x | x | x | x | x | x | x |  |  | x | x | x | x
15. Communications | Social media campaign - raising awareness | x | x | x | x | x | x | x |  |  | x | x | x | x
15. Communications | Publish external comms/information leaflets including information about LPS processes, (full list required by Schedule AA1 para. 14) | x | x | x | [6 empty] | x | x | x | x
15. Communications | Produce specific information for cared-for individuals currently on DoLS who will be transferring to LPS |  |  | x | [6 empty] | x | x
16. Transition | Decision about how to manage the current backlog | x | x | x | [5 empty] | x | x
16. Transition | Develop approach for triage and waiting lists in transition period | x | x | x | [6 empty] | x | x
17. Audit and Monitoring | Consider what outcomes for the cared-for person can be captured and monitored (including experience) to evidence successful implementation | x | x | x | x | x | x | x |  | x
17. Audit and Monitoring | Develop management information tools to monitor LPS performance | x | x | x | x | x | x | x |  |  | x | x | x | x
17. Audit and Monitoring | Regularly monitor and review processes to ensure compliance | x | x | x | x | x | x | x | [6 empty] | x
17. Audit and Monitoring | Produce regular information on any waiting list | x | x | x
17. Audit and Monitoring | Care plan reviews to ensure necessary detail is included | x | x | x | x | x | x | x | [6 empty] | x
17. Audit and Monitoring | Include LPS in future audit plans (clinical audit, internal audit, operational audit etc) | x | x | x | x | x | x | x |  |  |  | x | x | x | x